## Quality Committee Review Log
Quality Committee Review Log | This Quality Committee Review Log is an operational tool, distinct from the high-level Board Log, as it focuses on the tactical implementation and reliance on objective data for decision-making.
Meeting Date | Agenda Item / Topic | Data/Metric Presented? (Yes/No) | Metric Name & Result (If Yes) | Discussion Summary & Outcome | Required Action / Directive | Responsible Party | Evidence Strength
2025-10-15 | Post-Fall Huddle Compliance | Yes | Post-Fall Huddle Compliance Rate: 95% | Reviewed audit results; noted a 5% gap in evening shift documentation. Agreed the process is working. | Create 1:1 coaching for 3 nurses on the evening shift identified in the audit. | Nurse Educator | High
2025-11-19 | TJC High-Risk RFI EC.02.06.01 | No | N/A | Discussed the challenge of finding time to fix the key control issue. Focused on policy, not progress. | Escalate this RFI to the Executive Leadership Team as a persistent risk due to lack of facilities support. | Safety Officer | Low
2025-12-17 | Fall Rate Reduction Project Review | Yes | Fall Rate: 1.8 per 1,000 Pts/Days (Month 12) | Final review of the project. Goal met and sustained for 3 months. Commendation to the unit team. | Close out the QI project. Convert fall rate to a standard metric on the unit's monthly dashboard. | QI Specialist | High
2026-01-21 | New Restraint Policy Training | Yes | Training Completion Rate: 65% | Noted low completion rate. Acknowledged the system issue (link broken in email). | Resend training link and set a hard deadline for 100% compliance within 14 days. Report results at next meeting. | HR / Training Manager | Moderate

## Column Definitions
Column Title | Purpose
Data/Metric Presented? (Yes/No) | (New) Did the discussion rely on a documented performance measure, audit result, or run chart? This is a mandatory check.
Metric Name & Result (If Yes) | Records the name of the measure and the specific numerical result that was reviewed.
Discussion Summary & Outcome | A brief, factual statement of what was reviewed and the conclusion reached (e.g., "Goal met," "Gap identified").
Required Action / Directive | The specific, time-bound task the committee mandates to resolve the issue or sustain the gain.
Responsible Party | The specific individual or department accountable for the action.
Evidence Strength | High (Action based on clear data), Moderate (Action based on a detailed report/plan), or Low (Informational update only).