## Sustain & Validate List
Sustain and Validate List | This list tracks processes that are currently high-performing and well-monitored. The goal is to perform minimal, regular checks to ensure the system doesn't degrade.
Rank | Metric/Process | Current Compliance Rate | Monitoring Body | Last Reality Check Date | Sustainability Action | Next Audit/Tracer Date
1 | Post-Fall Huddle Completion Rate | 98% | Quality Committee | 2025-10-15 | Action: Move to quarterly review. Transfer primary data review to Unit Manager. | Q1 2026
2 | Universal Protocol (Time-Out) Compliance | 100% | Surgical Safety Committee | 2025-09-01 | Action: Maintain status quo. Conduct unannounced "Quick Tracers" on 5 cases per month. | Continuous
3 | Medication Labeling Policy Adherence | 99% | Pharmacy & Therapeutics | 2025-11-05 | Action: Metric integrated into annual competency sign-off. Reduce committee review to bi-annually. | Q2 2026

## Restart and Rescue List
Restart and Rescue List | This list tracks the most critical risks: High-risk TJC RFIs that show declining compliance, or where the monitoring loop has completely failed (no mention in minutes, no closure report found). This becomes the Urgent Survey-Readiness Plan.
Rank | High-Risk Issue/Metric | Source of Failure | Priority Level | Recovery Action & Owner | Target Completion | Evidence for Next Review
1 | Verbal Order Read-Back Compliance (PC.02.01.11) | Loop Broken: No minutes or closure report found in 18 months. | HIGH (Urgent) | Action: Immediately mandate a 10-chart audit across 3 units. Owner: Quality Director. | 30 Days | Audit Log and New QI Project Charter
2 | Key Control/Secured Doors (EC.02.06.01, EP 20) | Compliance Declining: Facilities delays (low-strength entries in log). | HIGH (Critical) | Action: CEO Intervention: Schedule a dedicated 15-minute meeting with Facilities Director and CEO to establish a hard fix deadline and resource approval. Owner: CNO. | 14 Days | CEO Meeting Minutes & PO for new hardware
3 | Restraint Assessment Documentation | Compliance Declining: Last reported 85% (below target). | MEDIUM | Action: Develop a 5-question "Reality Check" Tracer for nurse managers to use on 3 shifts this week. Owner: Nurse Educator. | 45 Days | Tracer Results and Remediation Plan
4 | Psychosocial Assessment Completion | Loop Broken: Training update failed; data monitoring ceased. | MEDIUM | Action: IT Director to implement a hard stop in the EMR to prevent incomplete documentation. Owner: IT Director. | 60 Days | IT Ticket Closure Report